## Main Gantt
Project Name: Wolverhampton Upgrade | [5 empty] | Todays Date: | 2023-12-05
Project Manager Name: | [5 empty] | Project Start: | 03/01/2023 Last Updated 04/12/23 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | P l a n G r i d E n d
WBS | Task Name | Team Leader | Start | Finish | Duration | Predecessors | Resource Names | Notes | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| Initial Setup and Theoretical Planning | [7 empty] | M: Initial Setup and Theoretical Planning; T: Analysis/Planning; T: #REF!; M: #REF!
1 | Product Localization Template |  | 2024-01-04 | 2024-02-07 | 25 Days
1.1 | Scope |  | 2024-01-04 | 2024-02-07 | 25 Days | bar: T to W
1.1.1 | Review business case |  | 2024-01-04 | 2024-01-05 | 2 Days |  | Project manager,Management |  | S: Review business case
1.1.2 | Estimate project undertaking (for example, volumes, details/extent of localization) |  | 2024-01-08 | 2024-01-12 | 5 Days | 3 | Project manager |  | S: Estimate project undertaking (for example, volumes, details/extent of localization)
1.1.3 | Prepare localization specification (feasibility, for markets) |  | 2024-01-15 | 2024-01-16 | 2 Days | 4 | Project manager |  | W: Prepare localization specification (feasibility, for markets)
1.1.4 | Estimate costs |  | 2024-01-17 | 2024-01-19 | 3 Days | 5 | Project manager | bar: W to F
1.1.5 | Identify risks |  | 2024-01-22 | 2024-01-23 | 2 Days | 6 | Project manager |  | W: Identify risks
1.1.6 | Secure project sponsorship |  | 2024-01-24 | 2024-01-24 | 1 Days | 7 | Management |  | T: Secure project sponsorship
1.1.7 | Define preliminary resources |  | 2024-01-25 | 2024-01-31 | 5 Days | 8 | Project manager |  | T: Define preliminary resources
1.1.8 | Define project communications matrix/methods |  | 2024-01-25 | 2024-01-29 | 3 Days | 8 | Project manager |  | T: Define project communications matrix/methods
1.1.9 | Secure core resources |  | 2024-02-01 | 2024-02-07 | 5 Days | 9 | Project manager |  | T: Secure core resources
1.1.10 | Scope complete |  | 2024-02-07 | 2024-02-07 | 1 Days | 11,10
Analysis/Planning
2 | Analysis/Planning |  | 2024-02-08 | 2024-04-01 | 38 Days
2.1 | Identify localization resources (internal and outsourced) |  | 2024-02-08 | 2024-02-14 | 5 Days | 12 | Project Manager HR Manager |  | T: Identify localization resources (internal and outsourced)
2.2 | Identify Components to be Localized |  | 2024-02-15 | 2024-02-21 | 5 Days |  | Project Manager HR Manager |  | T: Identify Components to be Localized
2.2.1 | Software Components |  | 2024-02-15 | 2024-02-21 | 5 Days |  |  |  | T: Software Components
2.2.1.1 | Setup |  | 2024-02-15 | 2024-02-20 | 4 Days | 15 | Programmer |  | T: Setup
2.2.1.2 | User interface |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Programmer |  | T: User interface
2.2.2 | User Assistance Components |  | 2024-02-15 | 2024-02-21 | 5 Days |  |  |  | T: User Assistance Components
2.2.2.1 | Online help, documentation, frequently asked questions (FAQs) |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Support Engineer |  | T: Online help, documentation, frequently asked questions (FAQs)
2.2.2.2 | User guide |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Support Engineer |  | T: User guide
2.2.3 | Marketing Components |  | 2024-02-15 | 2024-02-21 | 5 Days |  |  |  | T: Marketing Components
2.2.3.1 | Packaging |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | CMO |  | T: Packaging
2.2.3.2 | Brochures |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | CMO |  | T: Brochures
2.2.3.3 | Web content |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | CMO |  | T: Web content
2.2.4 | Ancillary Components |  | 2024-02-15 | 2024-02-21 | 5 Days |  |  |  | T: Ancillary Components
2.2.4.1 | Macros |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Project Manager |  | T: Macros
2.2.4.2 | Add-ins |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Project Manager |  | T: Add-ins
2.2.4.3 | Templates |  | 2024-02-15 | 2024-02-21 | 5 Days | 15 | Project Manager |  | T: Templates
2.2.4.4 | Identify components to be localized complete |  | 2024-02-21 | 2024-02-21 | 1 Days | 30,29,28,26,24,22,21,18,19,25 |  |  | T: Identify components to be localized complete
2.3 | Ensure file localizability |  | 2024-02-22 | 2024-02-28 | 5 Days | 31 | Project manager,Analyst,Localization engineer |  | T: Ensure file localizability
2.4 | Define localization processes |  | 2024-02-29 | 2024-03-13 | 10 Days | 32 | Project manager,Analyst,Localization engineer |  | T: Define localization processes
2.5 | Identify tools |  | 2024-02-29 | 2024-03-06 | 5 Days | 32 | Localization engineer,Analyst |  | T: Identify tools
2.6 | Test tools |  | 2024-03-07 | 2024-03-08 | 2 Days | 34 | Localization engineer |  | S: Test tools
2.7 | Document localization process |  | 2024-03-14 | 2024-03-15 | 2 Days | 35,33 | Localization engineer,Analyst |  | S: Document localization process
2.8 | Prepare risk management plan |  | 2024-03-18 | 2024-03-20 | 3 Days | 33,36 | International program manager,Project manager |  | T: Prepare risk management plan
2.9 | Define communication procedures |  | 2024-03-21 | 2024-03-22 | 2 Days | 37 | Project manager,International program manager |  | S: Define communication procedures
2.1 | Identify time constraints |  | 2024-03-21 | 2024-03-21 | 1 Days | 37 | Project manager,International program manager |  | F: Identify time constraints
2.11 | Identify key milestones |  | 2024-03-22 | 2024-03-22 | 1 Days | 39 | Project manager,Analyst |  | S: Identify key milestones
2.12 | Develop delivery timeline |  | 2024-03-22 | 2024-03-25 | 2 Days | 40 | Project manager |  | T: Develop delivery timeline
2.13 | Obtain approvals to proceed (for example, concept, timeline, budget) |  | 2024-03-25 | 2024-03-25 | 1 Days | 41,38 | Management,Project manager |  | T: Obtain approvals to proceed (for example, concept, timeline, budget)
2.14 | Secure required resources |  | 2024-03-26 | 2024-04-01 | 5 Days | 42 | Project manager |  | T: Secure required resources
2.15 | Analysis complete |  | 2024-04-01 | 2024-04-01 | 1 Days | 43
 | time axis 2024-01-01 to 2024-09-29
3 | Production |  | 2024-04-02 | 2024-05-06 | 25 days | bar: 2024-03-20 to 2024-03-21
3.1 | Software Components |  | 2024-04-02 | 2024-04-16 | 11 days |  |  |  | 2024-03-23: #REF!
3.1.1 | Localization Component - Setup |  | 2024-04-02 | 2024-04-16 | 11 days | bar: 2024-03-25 to 2024-03-26
3.1.1.1 | Review identified component functionality |  | 2024-04-02 | 2024-04-02 | 1 day | 44 | Programmer |  | 2024-03-29: #REF!
3.1.1.2 | Localize identified component |  | 2024-04-03 | 2024-04-09 | 1 wk | 49 | Programmer | bar: 2024-03-29
3.1.1.3 | Refine component based on quality assurance (QA) feedback |  | 2024-04-12 | 2024-04-15 | 2 days | 105 | Programmer | bar: 2024-04-01 to 2024-04-02
3.1.1.4 | Localization component setup complete |  | 2024-04-16 | 2024-04-16 | 0 days | 106 |  |  | 2024-04-05: #REF!
3.1.2 | Localization Component - User Interface |  | 2024-04-02 | 2024-04-16 | 11 days | bar: 2024-04-05 to 2024-04-08
3.1.2.1 | Review identified component functionality |  | 2024-04-02 | 2024-04-02 | 1 day | 44 | Localizer | bar: 2024-04-09 to 2024-04-10
3.1.2.2 | Localize identified component |  | 2024-04-03 | 2024-04-09 | 1 wk | 54 | Localizer |  | 2024-04-05: #REF!
3.1.2.3 | Refine component based on QA feedback |  | 2024-04-12 | 2024-04-15 | 2 days | 108 | Localizer | bar: 2024-04-05 to 2024-04-08
3.1.2.4 | Localization component - user interface complete |  | 2024-04-16 | 2024-04-16 | 0 days | 109 | bar: 2024-04-09 to 2024-04-10
3.1.3 | Software components complete |  | 2024-04-16 | 2024-04-16 | 0 days | 57 | bar: 2024-04-09 to 2024-04-10
3.2 | User Assistance Components |  | 2024-04-17 | 2024-05-01 | 11 days | bar: 2024-04-09 to 2024-04-10
3.2.1 | Localization Component - Online Help, Documentation, FAQs |  | 2024-04-17 | 2024-05-01 | 11 days | bar: 2024-04-09 to 2024-04-10
3.2.1.1 | Review identified component functionality |  | 2024-04-17 | 2024-04-17 | 1 day | 58 | Localizer | bar: 2024-04-15 to 2024-04-18
3.2.1.2 | Localize identified component |  | 2024-04-18 | 2024-04-24 | 1 wk | 61 | Localizer |  | 2024-04-22: #REF!
3.2.1.3 | Refine component based on QA feedback |  | 2024-04-29 | 2024-04-30 | 2 days | 111 | Localizer
3.2.1.4 | Localization component - online help, documentation, FAQs complete |  | 2024-05-01 | 2024-05-01 | 0 days | 112
3.2.2 | Localization Component - User Guide |  | 2024-04-17 | 2024-05-01 | 11 days
3.2.2.1 | Review identified component functionality |  | 2024-04-17 | 2024-04-17 | 1 day | 58 | Localizer
3.2.2.2 | Localize identified component |  | 2024-04-18 | 2024-04-24 | 1 wk | 66 | Localizer |  | 2024-04-24: #REF!
3.2.2.3 | Refine component based on QA feedback |  | 2024-04-29 | 2024-04-30 | 2 days | 114 | Localizer | bar: 2024-04-24
3.2.2.4 | Localization component - user guide |  | 2024-05-01 | 2024-05-01 | 0 days | 115 |  |  | 2024-04-26: #REF!
3.2.3 | User assistance components complete |  | 2024-05-01 | 2024-05-01 | 0 days | 69 | bar: 2024-04-26
3.3 | Marketing Components |  | 2024-04-02 | 2024-05-06 | 25 days | bar: 2024-04-29
3.3.1 | Localization Component - Marketing Materials |  | 2024-04-02 | 2024-04-16 | 11 days
3.3.1.1 | Review identified component functionality |  | 2024-04-02 | 2024-04-02 | 1 day | 44 | Localizer,Translator |  | 2024-05-01: #REF!
3.3.1.2 | Localize identified component |  | 2024-04-03 | 2024-04-09 | 1 wk | 73 | Localizer,Translator | bar: 2024-05-01
3.3.1.3 | Refine component based on QA feedback |  | 2024-04-12 | 2024-04-15 | 2 days | 117 | Localizer,Translator |  | 2024-05-03: #REF!
3.3.1.4 | Localization component marketing materials complete |  | 2024-04-16 | 2024-04-16 | 0 days | 75118 |  |  | 2024-05-04: #REF!
3.3.2 | Localization Component - Web Content |  | 2024-04-17 | 2024-05-01 | 11 days |  |  |  | 2024-05-21: #REF!
3.3.2.1 | Review identified component functionality |  | 2024-04-17 | 2024-04-17 | 1 day | 76 | Localizer,Translator | bar: 2024-05-21
3.3.2.2 | Localize identified component |  | 2024-04-18 | 2024-04-24 | 1 wk | 78 | Localizer,Translator |  | 2024-05-23: #REF!
3.3.2.3 | Refine component based on QA feedback |  | 2024-04-29 | 2024-04-30 | 2 days | 120 | Localizer,Translator | bar: 2024-05-23
3.3.2.4 | Localization component - web content |  | 2024-05-01 | 2024-05-01 | 0 days | 80121 |  |  | 2024-05-27: #REF!
3.3.3 | Marketing components complete |  | 2024-05-01 | 2024-05-01 | 0 days | 81 | bar: 2024-05-27
3.3.4 | Ancillary Components |  | 2024-04-02 | 2024-05-06 | 25 days |  |  |  | 2024-05-29: #REF!
3.3.4.1 | Localization Component - Macros |  | 2024-04-02 | 2024-04-16 | 11 days | bar: 2024-05-29
3.3.4.1.1 | Review identified component functionality |  | 2024-04-02 | 2024-04-02 | 1 day | 44 | Localizer,Translator |  | 2024-05-31: #REF!
3.3.4.1.2 | Localize identified component |  | 2024-04-03 | 2024-04-09 | 1 wk | 85 | Localizer,Translator
3.3.4.1.3 | Refine component based on QA feedback |  | 2024-04-12 | 2024-04-15 | 2 days | 123 | Localizer,Translator |  | 2024-06-04: #REF!
3.3.4.1.4 | Localization component - macros |  | 2024-04-16 | 2024-04-16 | 0 days | 124 | bar: 2024-06-04
3.3.4.2 | Localization Component - Add-Ins |  | 2024-04-17 | 2024-05-01 | 11 days |  |  |  | 2024-06-06: #REF!
3.3.4.2.1 | Review identified component functionality |  | 2024-04-17 | 2024-04-17 | 1 day | 88 | Localizer,Translator | bar: 2024-05-01
3.3.4.2.2 | Localize identified component |  | 2024-04-18 | 2024-04-24 | 1 wk | 90 | Localizer,Translator |  | 2024-05-03: #REF!
3.3.4.2.3 | Refine component based on QA feedback |  | 2024-04-29 | 2024-04-30 | 2 days | 126 | Localizer,Translator |  | 2024-05-04: #REF!
3.3.4.2.4 | Localization component - add-ins |  | 2024-05-01 | 2024-05-01 | 0 days | 127 |  |  | 2024-05-21: #REF!
3.3.4.3 | Localization Component - Templates |  | 2024-04-02 | 2024-04-16 | 11 days | bar: 2024-05-21
3.3.4.3.1 | Review identified component functionality |  | 2024-04-02 | 2024-04-02 | 1 day | 44 | Localizer,Translator |  | 2024-05-23: #REF!
3.3.4.3.2 | Localize identified component |  | 2024-04-03 | 2024-04-09 | 1 wk | 95 | Localizer,Translator |  | 2024-05-27: #REF!
3.3.4.3.3 | Refine component based on QA feedback |  | 2024-04-12 | 2024-04-15 | 2 days | 129 | Localizer,Translator | bar: 2024-05-27
3.3.4.3.4 | Localization component - templates |  | 2024-04-16 | 2024-04-16 | 0 days | 130 |  |  | 2024-05-29: #REF!
3.3.4.4 | Ancillary components complete |  | 2024-05-01 | 2024-05-01 | 0 days | 93 | bar: 2024-05-29
3.3.4.5 | Validate final released software (decisions on development cycle) |  | 2024-05-02 | 2024-05-06 | 3 days | 99,98 | Project manager,International program manager,Management |  | 2024-05-31: #REF!
3.3.5 | Development complete |  | 2024-05-06 | 2024-05-06 | 0 days | 99,98,100
#REF!
4 | Quality Assurance |  | 2024-04-10 | 2024-07-25 | 77 days | bar: 2024-06-04
4.1 | Localization Component - Setup |  | 2024-04-10 | 2024-04-16 | 5 days |  |  |  | 2024-06-06: #REF!
4.1.1 | Test component - setup |  | 2024-04-10 | 2024-04-11 | 2 days | 50 | Technical reviewer | bar: 2024-06-06
4.1.2 | QA review cycle |  | 2024-04-16 | 2024-04-16 | 1 day | 51 | Technical reviewer | bar: 2024-06-07
4.2 | Localization Component - User Interface |  | 2024-04-10 | 2024-04-16 | 5 days |  |  |  | 2024-06-11: #REF!
4.2.1 | Test component - user interface |  | 2024-04-10 | 2024-04-11 | 2 days | 55 | Technical reviewer | bar: 2024-06-11
4.2.2 | QA review cycle |  | 2024-04-16 | 2024-04-16 | 1 day | 56 | Technical reviewer |  | 2024-06-13: #REF!
4.3 | Localization Component - Online Help, Documentation, FAQs |  | 2024-04-25 | 2024-05-01 | 5 days | bar: 2024-06-13
4.3.1 | Test component - online help, documentation, FAQs |  | 2024-04-25 | 2024-04-26 | 2 days | 62 | Technical reviewer |  | 2024-06-15: #REF!
4.3.2 | QA review cycle |  | 2024-05-01 | 2024-05-01 | 1 day | 63 | Technical reviewer
4.4 | Localization Component - User Guide |  | 2024-04-25 | 2024-05-01 | 5 days |  |  |  | 2024-06-18: #REF!
4.4.1 | Test component - user guide |  | 2024-04-25 | 2024-04-26 | 2 days | 67 | Technical reviewer | bar: 2024-06-17
4.4.2 | QA review cycle |  | 2024-05-01 | 2024-05-01 | 1 day | 68 | Technical reviewer |  | 2024-06-18: #REF!
4.5 | Localization Component - Marketing Materials |  | 2024-04-10 | 2024-04-16 | 5 days | bar: 2024-06-17
4.5.1 | Test component - marketing materials |  | 2024-04-10 | 2024-04-11 | 2 days | 74 | Technical reviewer |  | 2024-06-18: #REF!
4.5.2 | QA review cycle |  | 2024-04-16 | 2024-04-16 | 1 day | 75 | Technical reviewer | bar: 2024-06-17
4.6 | Localization Component - Web Content |  | 2024-04-25 | 2024-05-01 | 5 days |  |  |  | 2024-06-19: #REF!
4.6.1 | Test component - web content |  | 2024-04-25 | 2024-04-26 | 2 days | 79 | Technical reviewer | bar: 2024-06-18
4.6.2 | QA review cycle |  | 2024-05-01 | 2024-05-01 | 1 day | 80 | Technical reviewer |  | 2024-06-20: #REF!
4.7 | Localization Component - Macros |  | 2024-04-10 | 2024-04-16 | 5 days | bar: 2024-06-20
4.7.1 | Test component - macros |  | 2024-04-10 | 2024-04-11 | 2 days | 86 | Technical reviewer |  | 2024-06-22: #REF!
4.7.2 | QA review cycle |  | 2024-04-16 | 2024-04-16 | 1 day | 87 | Technical reviewer
4.8 | Localization Component - Add-Ins |  | 2024-04-25 | 2024-05-01 | 5 days
4.8.1 | Test component - add-ins |  | 2024-04-25 | 2024-04-26 | 2 days | 91 | Technical reviewer | time axis 2024-01-01 to 2024-09-29
4.8.2 | QA review cycle |  | 2024-05-01 | 2024-05-01 | 1 day | 92 | Technical reviewer |  | 2024-04-23: #REF!
4.9 | Localization Component - Templates |  | 2024-04-10 | 2024-04-16 | 5 days
4.9.1 | Test component - templates |  | 2024-04-10 | 2024-04-11 | 2 days | 96 | Technical reviewer |  | 2024-04-25: #REF!
4.9.2 | QA review cycle |  | 2024-04-16 | 2024-04-16 | 1 day | 97 | Technical reviewer | bar: 2024-05-06
4.1 | Integration Testing |  | 2024-05-07 | 2024-05-15 | 7 days |  |  |  | 2024-05-09: #REF!
4.10.1 | Full component test |  | 2024-05-07 | 2024-05-13 | 1 wk | 130, 127, 124, 121, 118 | Technical reviewer |  | 2024-05-10: #REF!
4.10.2 | QA review cycle |  | 2024-05-14 | 2024-05-15 | 2 days | 132 | Technical reviewer | bar: 2024-05-13
4.11 | Sponsor Review |  | 2024-04-17 | 2024-05-16 | 22 days |  |  |  | 2024-05-14: #REF!
4.11.1 | Review component - setup |  | 2024-04-17 | 2024-04-17 | 1 day | 52 | Management,International program manager |  | 2024-05-16: #REF!
4.11.2 | Review component - user interface |  | 2024-04-17 | 2024-04-17 | 1 day | 57 | Management,International program manager | bar: 2024-05-13
4.11.3 | Review component - online help, documentation, FAQs |  | 2024-05-02 | 2024-05-02 | 1 day | 64 | Management,International program manager |  | 2024-05-14: #REF!
4.11.4 | Review component - user guide |  | 2024-05-02 | 2024-05-02 | 1 day | 69 | Management,International program manager |  | 2024-05-16: #REF!
4.11.5 | Review component - marketing materials |  | 2024-04-17 | 2024-04-17 | 1 day | 76 | Management,International program manager |  | 2024-05-17: #REF!
4.11.6 | Review component - web content |  | 2024-05-02 | 2024-05-02 | 1 day | 81 | Management,International program manager | bar: 2024-05-17
4.11.7 | Review component - macros |  | 2024-04-17 | 2024-04-17 | 1 day | 88 | Management,International program manager |  | 2024-05-22: #REF!
4.11.8 | Review component - add-ins |  | 2024-05-02 | 2024-05-02 | 1 day | 93 | Management,International program manager |  | 2024-05-22: #REF!
4.11.9 | Review component - templates |  | 2024-04-17 | 2024-04-17 | 1 day | 98 | Management,International program manager | bar: 2024-05-22
4.11.10 | Review integrated product |  | 2024-05-16 | 2024-05-16 | 1 day | 133 | Management,International program manager | bar: 2024-05-23
4.12 | Quality assurance complete |  | 2024-05-16 | 2024-05-16 | 0 days | 135, 136, 137, 138, 139 |  |  | 2024-05-24: #REF!
4.13 | Beta Testing |  | 2024-05-17 | 2024-07-02 | 33 days | bar: 2024-05-23
4.13.1 | Disseminate completed product |  | 2024-05-17 | 2024-05-21 | 3 days | 101145 | Management,International program manager |  | 2024-05-25: #REF!
4.13.2 | Obtain feedback |  | 2024-05-22 | 2024-06-18 | 4 wks | 147 | Management,International program manager
4.13.3 | Modify |  | 2024-06-19 | 2024-06-25 | 1 wk | 148 | Management,International program manager,Localization engineer
4.13.4 | Test |  | 2024-06-26 | 2024-07-02 | 1 wk | 149 | Management,International program manager |  | 2024-05-28: #REF!
4.13.5 | Complete |  | 2024-07-02 | 2024-07-02 | 0 days | 150 |  |  | 2024-05-29: #REF!
4.14 | Post-Project Review |  | 2024-07-03 | 2024-07-25 | 17 days | bar: 2024-05-29
4.14.1 | Review project information |  | 2024-07-03 | 2024-07-09 | 1 wk | 151 | Project manager |  | 2024-05-31: #REF!
4.14.2 | Finalize cost analysis |  | 2024-07-10 | 2024-07-12 | 3 days | 153 | Project manager | bar: 2024-05-31
4.14.3 | Analyze performance |  | 2024-07-15 | 2024-07-17 | 3 days | 154 | Project manager | bar: 2024-06-03
4.14.4 | Archive files |  | 2024-07-18 | 2024-07-19 | 2 days | 155 | Project manager |  | 2024-06-04: #REF!
4.14.5 | Document lessons learned |  | 2024-07-22 | 2024-07-23 | 2 days | 156 | Project manager | bar: 2024-06-05
4.14.6 | Distribute to team members |  | 2024-07-24 | 2024-07-25 | 2 days | 157 | Project manager |  | 2024-06-07: #REF!
4.14.7 | Post-project review complete |  | 2024-07-25 | 2024-07-25 | 0 days | 158 | bar: 2024-06-07
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
project start
[9 empty] | Initial Setup and Theoretical Planning | [41 empty] | 0 | [29 empty] | 0 | [40 empty] | #REF! | [62 empty] | #REF! | [19 empty] | #REF! | [53 empty] | 0
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
 | time axis 2024-01-01 to 2024-09-29
[9 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39

## OBD Breakdown
Agile OBD - Outcome Based Delivery (also MS Project Plan also)
OBD - Business Outcomes
EPIC: BO: 1. Agree on Business Outcomes and KPIs
User Story: BO: 1. Agree on Business Outcomes; Impact/Value, Objective, Initiative, Use Cases
User Story: BO: 2. Identify Business Outcome KPIs
User Story: BO: 3. Identify and Align with Key Stakeholders (LOB and IT) who have Ownership of the Outcomes
User Story: BO: 4. Identify Dependencies and Potential Risks to Business Outcomes
EPIC: BO: 2. Develop the Overall Success Plan
User Story: BO: 1. Build Consolidated 180-day Activity Plan
User Story: BO: 2. Establish and Staff the Leadership Team, e.g. Steering Committee
User Story: BO: 3. Define Roles and Responsibilities for Leadership Team
User Story: BO: 4. Develop Consolidated KPI Dashboard across all 6 Paths owned by EnableWay
User Story: BO: 5. Develop KPI Measurement Plan
User Story: BO: 6. Determine Cadence, Structure and Content of Review Meetings
User Story: BO: 7. Build Overall Success Plan
EPIC: BO: 3. Monitor and Manage
User Story: BO: 1. Hold Executive Business Reviews (e.g. Quarterly) to Track; Outcomes, KPI Dashboards, Dependencies, Risks
EPIC: BO: 4. Measure Business Outcomes
User Story: BO: 1. Measure the Business Outcomes and KPIs periodically
OBD - Technology Delivery
EPIC: TD: 1. Define MultiWay Platform Vision and Roadmap
User Story: TD: 1. Define the Vision for MultiWay Platform; Implementation Considerations (e.g. Cloud vs. On-Prem), Org Ownership, Non-Functional Requirements
User Story: TD: 2. Validate Vision with Relevant Enterprise Architecture Stakeholders and Operations Stakeholders
User Story: TD: 3. Define Key MultiWay Platform Milestones (incl. MVP) and Map to Overall Success Plan
User Story: TD: 4. Establish MultiWay Platform KPIs
User Story: TD: 5. Develop KPI Measurement Plan
EPIC: TD: 2. Design MultiWay platform architecture and implementation plan
User Story: TD: 1. Establish MultiWay Platform Architecture including; Deployment Arch, Infrastructure Arch, Operational Arch, Security Arch, Environments Model
User Story: TD: 2. Establish DevOps CI/CD Methodology
User Story: TD: 3. Define the Common Services Approach
User Story: TD: 4. Define MultiWay Platform Operational Model, e.g. tooling, monitoring
User Story: TD: 5. Define MultiWay Platform Test Plan, Functional and Non-Functional
User Story: TD: 6. Define MultiWay Platform Implementation Plan to Support Key Milestones
User Story: TD: 7. Define MultiWay Platform Upgrade Plan
User Story: TD: 8. Define MultiWay Platform DR Plan
User Story: TD: 9. Validate Compliance with Existing Corporate Standards, e.g. Architecture and Operations
EPIC: TD: 3. Prioritize IT Projects and Quick Wins
User Story: TD: 1. Build IT Project Backlog, Planned and Identified
User Story: TD: 2. Ensure IT Projects are Mapped to Business Outcomes in the Success Platform
User Story: TD: 3. Analyse Projects and EnableWay Prioritize Based on; Value, Business Criticality, Re-use Potential based on Business Domains
User Story: TD: 4. Identify Quick Wins
EPIC: TD: 4. Staff and Onboard the Project Teams
User Story: TD: 1. Schedule Projects based on Prioritization including Quick Wins
User Story: TD: 2. Staff and Onboard Project Teams; ACMe Training and Certification including Re-usability Concepts and API Led Connectivity
User Story: TD: 3. Build Project Plans
User Story: TD: 4. Engage with Enterprise Architecture and Operations Teams to Review Plans
User Story: TD. 5. Identify Project KPIs
User Story: TD. 6. Develop KPI Measurement
EPIC: TD: 5. Deploy MultiWay Platform
User Story: TD: 1. Install MultiWay Platform
User Story: TD: 2. Build and Launch MVP including Common Services, e.g. Security, Logging
User Story: TD: 3. Execute MultiWay Platform Test Plan
User Story: TD: 4. Transfer Ownership of the MultiWay Platform to Operations/Support Team
User Story: TD: 5. Set up DevOps CI/CD Pipelines
User Story: TD: 6. Onboard First Set of Projects
EPIC: TD: 6. Measure MultiWay Platform KPIs
User Story: TD: 1. Periodically Measure MultiWay Platform KPIs, e.g. Core Usage, Number of Deployments
User Story: TD: 2. Develop Improvement Recommendations, e.g. Improve Isolation of Environments
EPIC: TD: 7. Define Reference Architecture
User Story: TD: 1. Define Reference Architecture Document to Support Prioritized Use Cases and Serve as the Baseline Document for Future Projects
EPIC: TD: 8: Launch Initial Projects and Quick Wins
User Story: TD: 1. Deliver on Projects, e.g. in Accordance with Best Practices and API Blueprint
User Story: TD: 2. Iterative Development Sprints Including; Requirements Planning (Functional and Non-Functional), Config. And Build (including CI/CD), Testing (Unit, Performance), Sprint Demos, Feedback Reviews
User Story: TD: 3. Deploy and Transition Project
EPIC: TD: 9: Measure Project KPIs
User Story: TD: 1. Measure Project KPIs
User Story: TD: 2. Develop Improvement Recommendations, e.g. Increase Use of Automation
OBD - Organisational Enablement
EPIC: OE: 1. Assess Integration Capabilities
User Story: OE: 1. Assess Organizations Capabilities Across the Following Dimensions; Strategy Organization, Governance, Architecture, Delivery, Operations, Community and Evangelizing
EPIC: OE: 2. Establish the EnableWay Operating Model
User Story: OE: 1. Agree on EnableWay Mission and Charter
User Story: OE: 2. Determine EnableWay Org. Model for e.g. Decentralized Delivery Model
User Story: OE: 3. Agree on the Individual EnableWay Team Roles and Responsibilities, e.g. EnableWay Lead
User Story: OE: 4. Determine Staffing Model (Dedicated vs. Virtual FTEs)
User Story: OE: 5. Agree on Funding Model
User Story: OE: 6. Staff Core EnableWay Team
User Story: OE: 7. Educate and Train the Core EnableWay Team in API-Led Connectivity and EnableWay
User Story: OE: 8. Build Detailed Workplans for EnableWay Team to Execute On
User Story: OE: 9. Establish MultiWay Exchange as the Central Hub for Saving, Sharing and Discovering Common Assets
User Story: OE: 10. Build Asset Feedback Model
User Story: OE: 11. Define KPIs for Measuring Consumption, Developer Engagement and Productivity
User Story: OE: 12. Define Measurement plan for KPIs, e.g. How to Gather Data, How Often
EPIC: OE: 3. Onboard ACMe
User Story: OE: 1. Appoint Overall Support Contacts, should be ACMe Certified Developers
User Story: OE: 2. Ensure Support Accounts are Provisioned to Your Designated Support Contracts
User Story: OE: 3. Set-up Onboarding Session with ACMe Customer Success Team
EPIC: OE: 4. Determine the Internal Support Operating Model
User Story: OE: 1. Agree on Required Internal MultiWay platform support capability and who will be responsible, e.g. EnableWay team
User Story: OE: 2. Align on the issue resolution and escalation process, e.g. first level issue tickets handled internally
User Story: OE: 3. Agree on roles required and training required by role
User Story: OE: 4. Agree on Key Support APIs to Measure
User Story: OE: 5. Develop KPI Measurement Plan
EPIC: OE: 5. Agree on Initial Roles
User Story: OE: 1. Aggregate the initial roles required including; EnableWay Roles, Project Team roles, Platform Roles, Support Roles, Partner Roles
User Story: OE: 2. Assign the training paths for each role, e.g. architect path
User Story: OE: 3.Appoint training co-ordinator to build training plan and track adherence
User Story: OE: 4. Develop Training KPIs
EPIC: OE: 6. Train the Initial Teams
User Story: OE: 1. Build Training Plan
User Story: OE: 2. Ensure Participants have satisfied prerequisites for training classes
User Story: OE: 3. Train and Certify the Initial Teams
EPIC: OE: 7. Build and Publish Foundational Assets
User Story: OE: 1. Define the Enterprise Domains to Align APIs
User Story: OE: 2. Build the API Roadmap dependent on project prioritization stream
User Story: OE: 3. Build and Publish Foundational set of Re-usable Assets, e.g. API templates, common services etc.
User Story: OE: 4. Build Foundational set of Best Practices, e.g. Coding and Operating Guidelines, Common API Patterns etc.
User Story: OE: 5. Identify Public Assets to make Available in Exchange
User Story: OE: 6. Define Onboarding / Onramp process to enable developers to get started on ACMe, Discover Assets and Consume Assets
User Story: OE: 7. Onboard Project Teams
EPIC: OE: 8. Measure EnableWay KPIs
User Story: OE: 1. Measure and Report on the EnableWay KPIs as part of an Integrated Dashboard
User Story: OE: 2. Develop Improvements Recommendations, e.g. plan hackathon to drive re-use
EPIC: OE: 9. Staff, Train and Launch Team
User Story: OE: 1. Identify the Team Members
User Story: OE: 2. Train the team members
User Story: OE: 3. Launch the Support Team
EPIC: OE: 10. Publish Support Guidance and Self-Service Materials
User Story: OE: 1. Build and Publish Support Process Flows Including Escalations
User Story: OE: 2. Build and Publish Guidelines to Interact with Internal Support Team, including what data is required per type of issue / incident
User Story: OE: 3: Build and Publish Self-Service Support Documentation, e.g. KB Knowledge Base Articles
User Story: OE: 4. Ensure broad access to external ACMe Resources
EPIC OE: 11: Measure Support KPIs
User Story: OE: 1. Measure Supports KPIs
User Story: OE: 2: Develop Improvement Recommendations, e.g. Enhance Troubleshooting Guides, EnableWay modifications, re-usable asset improvements, training plan
EPIC: OE: 12. Develop the Broader Training Plan
User Story: OE: 1. Aggregate the broader roles required including; EnableWay Roles, Project Team Roles, Platform Roles, Support Roles, Partner Roles
User Story: OE: 2. Assign the training paths for each role, e.g. architect path
User Story: OE: 3. Build training plan
User Story: OE: 4. Ensure participants have satisfied pre-requisites for training
User Story: OE: 5. Train and certify the broader team(s)
EPIC: OE: 13. Launch Experiential Learning Opportunities
User Story: OE: 1. Participate in the ACMe champions program
User Story: OE: 2. Participate in ACMe webinars and API Workshops
User Story: OE: 3. Participate in Developer Workshops
User Story: OE: 4. Attend ACMe Connect and Customer Summits
User Story: OE: 5. Join the ACMe Developer Forums
User Story: OE: 6. Join the ACMe Blog
User Story: OE: 7. Join the ACMe meet up groups by Geography
EPIC: OE: 14. Conduct Skills Assessment
User Story: OE: 1. Measure Training KPIs
User Story: OE: 2. Conduct Skills Assessment to determine gaps in training classes taken and certifications achieved
User Story: OE: 3. Develop training improvement recommendations

## Tasking
# | Some Task Names (taken from the MS Project MPP files for those who do not have MS Project). Excel planners are included in this folder.
1 | MS Project Plan Template
2
3 | Project key milestones (amend Generic MS Plan: Start Date, Sprint and Ceremony details (if Agile is being used) and tasks based on project context)
4 | Start Phase
5 | Execute Phase
6 | Close Phase
7
8 | Agile Ceremonies
9 | Sprint Planning Meeting
10 | Daily Scrum / Stand Up Meeting
11 | Sprint Review / Demonstration Meeting
12 | Sprint Retrospective Meeting
13
14 | Sprints Overview (2-week sprints - amend number and length as appropriate)
15
16 | Key Project Dependencies (to complete...)
17 | CLIENT: Dependency 1 (e.g. Access Requirements)
18 | CG: Dependency 2 (e.g. Architect assigned for Workshops)
19 | CG: Dependency 3 (e.g. Project artefacts required to pass client governance Gateways, add each client Gateway as a dependency)
20 | CLIENT: Dependency 4 (e.g. Client obligations, Licenses, Hardware, Networking, Ports)
21 | 3rd PARTY: Dependency 5 (e.g. database connection acquired) etc…
22
23 | Key Project Milestones + Project Deliverables (Green items in main plan to complete...)
24
25 | Key Meetings
26
27 | Inception and Elaboration
28 | START: Inception & Elaboration Tasks
29 | Client PO Created for Project
30 | Workshops and Analysis (to complete...)
31 | Workshop 1
32 | Risk Workshop
33 | Workshop 3 etc…
34 | Verify any Change Freeze Dates with Client
35 | Verify if Client Portals Require Updating for Document Deliverables
36 | Confirm Project Scope & User Stories / Requirements / Client Sign-Off Complete (Milestone)
37 | Confirm Client and Third-Party Contact List
38 | Produce High Level Architecture (HLA) Document
39 | Request HLA Review
40 | HLA Client, Supplier Sign-Off Complete (Milestone)
41 | Produce High Level Design (HLD) Document + UX / UI (PDA), Failover as required
42 | HLD Client Walkthrough
43 | Request HLD Review
44 | Walkthrough & Review of Detailed Plan
45 | HLD Client Sign-Off Complete (Milestone)
46 | Produce High-Level POAP from Detailed Plan / Share with Client
47 | Document Non-Functional Requirements (NFRs)
48 | NFRs Client Sign-Off Complete (Milestone)
49 | Security Plan Document, Networking, Ports etc.
50 | Request Security Plan Review
51 | Security Plan Document Client Sign-Off Complete (Milestone)
52 | Monitoring Requirements Design Document
53 | Monitoring Requirements Document Sign-Off (Milestone)
54 | Produce Low Level Design(s) (LLD) Document + UX / UI (PDA) as required
55 | LLD(s) Client Walkthrough
56 | Request LLD(s) Review
57 | LLD(s) Client, Supplier Sign-Off Complete (Milestone)
58 | Produce Test Strategy Document (SIT, PVT, PEN, OAT, UAT) + Automated Test & CI Approach
59 | Request Test Strategy Document Review
60 | Test Strategy Document Revisions
61 | Test Strategy Document Client Sign-Off Complete (Milestone)
62 | Establish the Product Backlog (Milestone)
63 | Define / Setup Project Environment (modify as appropriate...)
64 | Acquire Licenses
65 | Acquire any Certificates required
66 | Address any Firewall requirements (RFCs)
67 | Creation of Deployment Policy for SIT, Pre-Prod(?) and Prod
68 | Development
69 | Test (ST, SIT)
70 | Pre-Production(?)
71 | Production...
72 | Confirm Access to Environments as appropriate
73 | Set-Up Database for Environments as required
74 | Set-Up Test Tools
75 | Project Environments(s) Set-Up Complete (Milestone)
76 | Agree Definition of Ready (DoR)
77 | Agree Definition of Done (DoD) (Milestone)
78 | Create Initial Architecture
79 | Identify Risks and Mitigation Strategies
80 | Define Engineering Standards
81 | Request Engineering Standards Client Sign-Off Complete (Milestone)
82 | Produce and Agree Release Level Schedule (Milestone)
83 | END: Inception & Elaboration Tasks
84
85 | Construction (Build) and Test
86 | START: Constructions Tasks
87 | Sprint 1 (plan in approved release cycles as required by client...)
88 | Add User Stories from Sprint Backlog if required...
89 | Sprint 2
90 | User Stories
91 | Sprint 3
92 | User Stories
93 | Sprint 4
94 | User Stories
95 | Sprint 5 (add all Sprints to complete...)
96 | User Stories
97
98 | System Integration Testing (SIT) Cycles
99 | SIT Test Plan Creation (TRAM)
100 | SIT Test Plan Review
101 | SIT Test Plan Revisions, Client Sign-Off (Milestone)
102 | SIT Draft Implementation Plan
103 | SIT Implementation Plan Approved, Client Sign-Off
104 | SIT User Accounts Added
105 | SIT Raise Request for Change (RFC)
106 | SIT Verify Security Keys / Firewalls have been addressed
107 | SIT, if required, incorporate Supplier Deliverables
108 | SIT Build Release Package
109 | SIT Deploy Release Package
110 | SIT Test Tools Configure / Test Harness / Stubs
111 | SIT Test Scripts / Cases & Test Data Set-Up
112 | SIT Smoke Test (prove deployment, evidence)
113 | SIT Regression Testing(?)
114 | SIT Cycle 1 (add cycles as required)...
115 | SIT Testing 1
116 | SIT Bug fixes
117 | SIT Test Results Evidence
118 | SIT Test Exit Report Produced
119 | SIT Complete, Sign-Off (Milestone)
120
121 | Penetration (PEN) / Performance (PVT) Testing
122 | PVT Volumetrics Agreed with Client
123 | PEN / PVT Verify Security Keys / Firewalls
124 | PEN / PVT Test Plan Creation
125 | PEN / PVT Test Plan Review
126 | PEN / PVT Test Plan Revisions, Client Sign-Off
127 | PVT Tool Set-Up
128 | PEN / PVT Test Scripts
129 | PEN / PVT Test Cycle + Fixes
130 | PEN / PVT Test Results Evidence
131 | PEN / PVT Complete, Sign-Off (Milestone)
132 | PEN / PVT Test Exit Report Produced
133
134 | Operational Acceptance Testing (OAT)
135 | OAT Test Plan Creation
136 | OAT Test Plan Review
137 | OAT Test Plan Revisions, Client Sign-Off
138 | OAT Scripts
139 | OAT Testing + Fixes
140 | OAT Test Results Evidence
141 | OAT Test Exit Report Produced
142 | OAT Complete, Sign-Off (Milestone)
143
144 | User Acceptance Testing (UAT)
145 | UAT Scripts
146 | UAT Testing + Fixes
147 | UAT Complete, Sign-Off (Milestone)
148 | END: Construction Tasks
149
150 | Transition
151 | START: Transition Tasks (add any Client / Quality GATEs)
152 | Conduct Customer Training
153 | Plan Project Handover
154 | Handover Support Documentation
155 | Deployment Phase
156 | Transition Planning
157 | Knowledge Acquisition Plan
158 | KT Approach
159 | Create and Agree Transition Plan with Client (Milestone)
160 | Initiate Risk and Issue Management
161 | Quality Gate Criteria
162 | Agree RACI for Transition Team
163 | Produce / Update Client Operational Readiness Procedures
164 | ORR Client Sign-Off, Completion (Milestone)
165 | Raise CRs for 3rd Party Changes
166 | Confirm Deployment Schedule with 3rd Parties
167 | ORR Completion with Client
168 | Raise CR / RFC for Deployment
169 | Deploy into Production
170 | Review Release Note Detailing Platform Specifications, User Accounts etc.
171 | Raise CR to Apply
172 | Apply Release Note to Build Production
173 | Update Firewall Rule Spreadsheet
174 | Request Production User accounts
175 | Raise Firewall RFC Requests
176 | Confirm Firewall Changes in Production (Milestone)
177 | Confirm Security / Key Updates Applied
178 | Raise RFCs for Suppliers in Production
179 | Confirm Supplier Changes Made
180 | Check Release Notes and Create Implementation Plans for Deployment
181 | Create CR / RFC for Deployment
182 | Complete Step by Step Walkthrough of Deployment Plan (Milestone)
183 | Amend Plan Following Walkthrough
184 | Confirm Dates and Readiness of Suppliers for Deployment
185 | Complete Build, Database Table Creation and Config/Software Deployment
186 | Complete Smoke Testing with Supplier Systems
187 | Deployment Completed (Milestone)
188 | Create Release Deployment Exit Report
189 | Review Release Deployment Exit report
190 | Release Deployment Exit report Sign-Off (Milestone)
191 | Cutover to Production
192 | Cutover scoping and planning
193 | CR Approved by Client
194 | Confirm Cutover Approach with Client
195 | Agree Cutover Approach with Suppliers
196 | Confirm Cutover Business Testing requirements
197 | Create Final Cutover Plan / Implementation Plan
198 | Cutover Plan Review
199 | Cutover Plan Revisions
200 | Cutover Plan Client Sign-Off, Completed (Milestone)
201 | Cutover Dress Rehearsals
202 | Detailed Cutover Plan Walkthrough
203 | Dress Rehearsal Prep
204 | Dress Rehearsal 1
205 | Dress Rehearsal 1 Follow Up Meeting
206 | Dress Rehearsal 2
207 | Dress Rehearsal Follow Up Meeting
208 | Confirm Go Live Readiness (Milestone)
209 | Cutover
210 | Agree Readiness for Cutover
211 | Raise CR
212 | Cutover Day - see separate Implementation Plan
213 | Cutover Complete
214 | Cutover evidence, verification and monitoring
215 | Cutover Sign-Off by the Client (Milestone)
216 | Transition to support and ELS
217 | Set-Up Weekly Transition and Handover Meetings
218 | Complete Transition to Support Activities
219 | ELS Period
220 | ELS Period End (Milestone)
221 | Post Implementation Assessment
222 | Transition Sign-Off (Milestone)
223 | Transition Closure Report
224 | END: Transition Tasks
225 | Project Mobilise / Inception
226 | Project Mobilise / Inception START
227 | SoW approved, Governance agreed
228 | Baseline Plan, produce Exit & KT plan (DOS)
229 | Agree Alpha scope & solution approach doc
230 | Agree iteration heartbeat for Agile delivery
231 | Book tech. workshops for arch. approach
232 | XY present work flows & user stories
233 | Review and feedback on all XY Project documents + prep. HL LA sessions plan
234 | Draft proj. schedule & resource plan
235 | Agree Implementation Plan
236 | Agree Security Management Plan (GDPR)
237 | Agree High Level design document
238 | Agree detailed acceptance criteria with XY
239 | XY License Dependency: Set-up Dev, Pre-Prod&Prod environments including prod. installs
240 | Agree Agile Def. of Ready (DOR) and DOD
241 | Product Owner Prioritise backlog
242 | Task n
243 | Task n+1
244 | Task n+2 etc.
245 | Project Mobilise / Inception END
246
247 | Project Elaboration (Design)
248 | Project Elaboration START
249 | Workshops: Architecture, DR, Testing, DevOps
250 | Approve plan and approach for LA engagement
251 | User Research/ Experience (UX) laboratories and feedback gathering engagement sessions - Doc
252 | Service Design and Support document started
253 | Agree HL Architecture Document, agree all NFRs
254 | Agree entity and database design, data model
255 | Agree and document Web interfaces and API connection standards and frameworks
256 | Agree DevOps strategy and CI/CD preparation
257 | Agree Test Strategy Document
258 | Refine prioritised Alpha user stories
259 | Agree UX approach, align with WCAG principles
260 | Prep Portal, CRM Test Approach & Plans (Alpha)
261 | Book Alpha Assessment ahead of build
262 | Create subscriptions, network, user permissions
263 | Plan in official MS Dynamics twice yearly updates (April and October currently)
264 | Workshops
265 | Agree NFRs
266 | Agree Security Approach
267 | Agree Test Strategy
268 | Agree Agile DoR / DoD
269 | Task n
270 | Task n+1
271 | Task n+2 etc.
272 | Project Elaboration END
273
274 | Project Construction (Build & Test)
275 | Project Construction START
276 | Task n
277 | Task 2 (Alpha)
278 | Approved Alpha Development
279 | Finalise GDS Standard Service Design
280 | Stakeholder Engage & Testing Planning
281 | Interactive prototype UI interface with users – AA, Client & Provider portals
282 | Bilingual prototype of UI & templates
283 | Progress prototype integration of Client Gateway and also:
284 | SAP, Objective and Notify integrations
285 | Management Information (MI) Power BI (first set) based on approved reports
286 | Alpha Build Testing CI/CD/TDD
287 | Update Client content team and stakeholders on progress with Agile stand-ups and show & tells, look at ASE booking
288 | Agree on functions to be taken forward into Beta and finalised (GDS)
289 | Prepare the Beta business proposal
290 | Task 3 (Beta)
291 | Approved Beta Development items plus bilingual translations booked – continue with User Research, plan in official MS Dynamics upgrade
292 | Finalise prototypes and integration from Alpha
293 | Complete approved MI reports
294 | Bilingual translations integrated
295 | SIT and Accessibility Test Plans
296 | SIT Test Cycles and Test Exit Report
297 | PEN (XY) / PVT Test Cycles and Test Exit Report
298 | Operational Acceptance Test Plan (OAT)
299 | OAT Test Cycles and Test Exit Report
300 | UAT Test Support and Sign-off
301 | Remediation Activities for above testing
302 | Align Client team pre Public Beta (GDS)
303 | Approve Pilot Planning approach
304 | Beta assess, publish accessibility page (GDS)
305 | Progress Training Planning and Development
306 | Maintain Beta Dashboard & Performance Mets.
307 | Testing
308 | SIT Testing
309 | PVT Testing
310 | OAT Testing
311 | UAT Testing
312 | UAT Testing Sign-Off
313 | Project Construction END
314
315 | Pilot
316 | Project Pilot START
317 | Complete Training Planning & Development and start rollout to LAs
318 | Support platforms and code / tools
319 | Prep. Plan for remediation phase & team effort / tasks
320 | Minor code / config fixes ahead of remediation phase
321 | Official MS Dynamics upgrade release
322 | Review perf. metrics and feedback
323 | Task n
324 | Task n+1
325 | Task n+2 etc.
326 | Project Pilot END
327
328 | Remediation and Test Phase
329 | Project Remediation and Test START
330 | SIT Test Cycles and Test Exit Report
331 | PEN (XY) / PVT Testing Cycles & Test Exit Report
332 | OAT Test Cycles & Test Exit Report
333 | Plan in UAT with XY
334 | UAT Test Support and Sign-off
335 | Remediation Activities for above
336 | Finalise rollout of training package to LAs and sign-off
337 | Task n
338 | Task n+1
339 | Task n+2 etc.
340 | Project Remediation and Test END
341
342 | Project Transition & ELS Phase
343 | Project Transition START
344 | Go-Live Preparation
345 | Client Operational Readiness Procedures
346 | Confirm Deploy Schedule to all stakeholders
347 | Prod Complete Smoke testing and exit reports
348 | Create & Approve Final Cutover/ Implement. plan
349 | Cutover Dress Rehearsals / Confirm Go-Live
350 | 21st Sept. - Cutover and Verification plus Monitor
351 | Book live assessment GDS
352 | Procure support phase
353 | Approve HL plan for transition
354 | Transition to Live
355 | Support platforms & code
356 | Confirm KT Objectives
357 | Identify relevant areas of knowledge and objects
358 | Identify team members for KT and assign roles
359 | Perform KT assessment
360 | Define team for Knowledge Transfer (KT) enablers
361 | Finalize KT plan
362 | Knowledge Transfer to XY agreed Support Partner in booked sessions
363 | Interim non SLA based 2nd and 3rd line support
364 | KT sign-off and exit
365 | Plan Project Handover
366 | Agree KT Approach
367 | Task n
368 | Task n+1
369 | Task n+2 etc.
370 | Deploy to Production
371 | ELS
372 | Project Transition END
373
374 | <<< Project END >>>